## Sheet1
Task | Start Date | Duration | End Date
Set up User Login and basic Home page | 2016-10-10 | 13 | 2016-10-23
Submission Form for Recipes | 2016-10-23 | 7 | 2016-10-30
Set up Home Page | 2016-10-30 | 7 | 2016-11-06
Create Search Page for Recipes | 2016-11-06 | 7 | 2016-11-13
Fine Tune Search, homepage and Form Submission | 2016-11-13 | 7 | 2016-11-20
Fine tune, if time, implement Comments Section and Instagram Feed for homepage (maybe as a side bar on all pages?) | 2016-11-20 | 7 | 2016-11-27
More fine tuning of most important aspects of website. Make website more visually pleasing. Create more options for users, such as food profiles and preferences. | 2016-11-27 | 7 | 2016-12-04